## Sheet1
Project Management Plan(PMP)
Task Name | Start | End | Duration (days) | Responsible | Reviewed by
Requirment collection | 2017-11-25 | 2017-11-27 | 2 | Omour Faruq | Mahedee
Prepare user story | 2017-11-28 | 2017-12-02 | 4 | Omour Faruq | Mahedee
Prepare HLD | 2017-12-01 | 2017-12-03 | 2 | Omour Faruq | Mahedee
Prepare LLD | 2017-12-03 | 2017-12-09 | 6 | Omour Faruq | Mahedee
Coding | 2017-12-10 | 2017-12-30 | 20 | Omour Faruq, Mahedee | Omour Faruq
Testing | 2017-12-15 | 2017-12-31 | 16 | Omour Faruq, Mahedee | Omour Faruq
Deployment | 2018-01-01 | 2018-01-02 | 1 | Omour Faruq, Mahedee | Omour Faruq